## Technical Debt
Technical Debt
Each team should submit two copies: One will be completed by the Quality Focal Point and the other one will be completed by the team.
Describe technical debt of your project :
| 1. Please describe your technical debt in Description | 4. Answer Yes/No on Has it been fixed?
| 2. Catgorize the technical debt based on Category 1 dropdown listbox | 5. If yes, how long did you spend(in hours), if not how long you are you estimating it will take to fix(in hours)?
| 3. Catgorize the technical debt based on Category 2 dropdown listbox | 6. Explain how did you fix it, or your mitgation plan if not fixed.
7. Report No of weeks active.
If you report the debt previously, please update its current status.
List your technical debt
# | Description | Category1 | Category2 | Has it been fixed? | How did you fix it/mitgation plan | No. of weeks active | Reckless _Deliberate | Life Cycle Management Shortfalls | Yes
1 | Not properly controlling source codes. Different form other groups, we are extending some functions from an iOS application. Due to non-disclosure agreement, we cannot put all of our codes on the GitHub. However, it is infeasible to copy and paste program continuously when two people write codes in same file simultaneously. | Methods, Processes and Tools (MPT) Shortfalls | Reckless _Deliberate | Yes | Thanks for USC account / ID, we have capability to use USC Enterprise GitHub which allows us to create private safe repository for our project. By doing so, we are not only able to manage our codes in USC Enterprise GitHub blameless, but able to prevent others access. | 5 | Reckless_Inadvertent | Personnel Shortfalls | No
2 | incompatible programs from different developers. Due to the large scale of this project, we have divided the entire project to many small tasks and assigned them to each individual guys. However, though we have agreed the workflow for the system, there still exist several conflicts when we merged our codes. | Life Cycle Management Shortfalls | Prudent_Inadvertent | No | Every two developers are ought to make comprehensive test cases during integration testing. | 5 | Prudent_Deliberate | Methods, Processes and Tools (MPT) Shortfalls
3 | Lack of reasonable test cases that make the system bug-free. This project is a one-semester project and requires plenty of functions. In order to demonstrate a runnable application before midterm, we didn’t follow the TDD process at the beginning. | Methods, Processes and Tools (MPT) Shortfalls | Reckless _Deliberate | No | The off-campus student is responsible for validation and testing. Even though he is not totally familiar with what we have accomplished so far, we will have a meeting together and discuss our achievement, achieving test cases for our project. | 7 | Prudent_Inadvertent
4
5
6
7
8
9
10

## Category1_Examples
Description | Examples
Life Cycle Management Shortfalls: | •Debt resulted from schedule pressure due to scope creep where additional features are added without altering the project scope and schedule.
This includes any debt resulted from the software life cycle management shortfalls such: budgeting, requirements, contracts, scheduling, etc. | •Debt resulted from a third-party-estimate where a technical lead make an ignorant- estimation on how long it will take and cost to developed and the actual team are held responsible for these estimation.
•This might include not preforming an automated testing due to schedule pressure, having duplicated code since there is no time to refactor,etc.
Personal Shortfalls:
This includes any debt resulted from people shortfalls | •Debt resulted from the project team such as adding or removing a team member.
such as: not having enough experience, change in team composition,etc. | •Debt resulted from the project team skills such as not having enough experience with the development language.
•This might include: Delaying unit testing until the new tester join the team, not preforming unit testing due to lack of experience.
Methods, tools, and process Shortfalls:
This include any debt resulted from Methods, tools, and process Shortfalls: such as tools limitations, process nature, etc. | •Debt resulted from tool limitation such as the inability to integrate with the API.
• Debt resulted from the process such as : not testing the code until the last minute since we are using waterfall
•This might include: delaying testing due to the process, delaying integration, not following the architecture specification due to language limitations

## Technical Debt Example
Technical Debt
Each team should submit two copies: One will be completed by the Quality Focal Point and the other one will be completed by the team.
Describe technical debt of your project :
| 1.Please describe your technical debt in Description | 4.Answer Yes/No on Has it been fixed?
| 2. Catgorize the technical debt based on Category 1 dropdown listbox | 5.If yes, how long did you spend(in hours), if not how long you are you estimating it will take to fix(in hours)?
| 3. Catgorize the technical debt based on Category 2 dropdown listbox | 6. Explain how did you fix it, or your mitgation plan if not fixed.
7.Report No of weeks active.
If you report the debt previously, please update its current status.
List your technical debt
# | Description | Category1 | Category2 | Has it been fixed? | How did you fix it/mitigation plan | No. of weeks active | Reckless _Deliberate | Life Cycle Management Shortfalls | Yes
1 | Due to time constraint, we will stop working on the French language option for this release even though the company will open a store in France in 3 years. | Life Cycle Management Shortfalls | Prudent_Deliberate | No | We are working on the English version, and will provide the client with a detailed technical explanation on how to support other languages | 10 | Reckless_Inadvertent | Personnel Shortfalls | No
2 | [6 empty] | Prudent_Deliberate | Methods, Processes and Tools (MPT) Shortfalls
3 | [6 empty] | Prudent_Inadvertent
4
5
6
7
8
9
10