## Risk
Top Project Risks as of 11/15/20176
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
1 | 2 | It is highly possible that we couldn’t finish our project as the client desired | The Client changed his idea comprehensively 1 week ago | Try to develop as much as functions as we could due to the lack of time | 7 | 3 | 21 | The client, he just changed his idea after talking with some new team members. | 2
2 | 3 | The off-campus student may misunderstand or don’t know our project clearly. | we don’t have change to meet in person and we found it was hard to communication with a virtual guy. | He has started to code and we have talked a lot in Slack. we thought he should have a better understand of the problem domains and of what we are building. | 5 | 5 | 15 | We have talked with den student more frequently in Slack | 9
3 | 1 | The score system may not feasible | We have expected a lot for the challenge feature but we don’t know whether it is enough attractive | 1) We should simplify the functionality 2) We should start to develop it even if we don’t have sufficient users’ feedback | 2 | 5 | 10 | We have empowered some simply rank system in our system | 6
4
5
6
7
8
10

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Vincent had a family emergency and was unavailable. | Kept updating our progress to make sure that he could catch up with our project
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Most of our team members are not good at speaking Engish | More practice and communication
2
3
4
5