## SLOC
Team Number: | 4
Week: | 1
Program Size (SLOC) | Actual
Base | N/A
Added | N/A
Deleted | N/A
Modified | N/A
Reused | N/A
From COTS | N/A
Total New SLOC | N/A

## COTS
List of third-party components being considered for use in the system as of 09/21/2016
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
ReactJS | Front-End | JavaScript | Framework for JS |  | 1
NodeJS | Front-End | JavaScript | Framework for JS |  | 1
Spring Boot(Java) | Back-End Java Framework | Java (Version8) | Framework for Java |  | 1
Java Persistence(JPA) | Database Connector | N/A |  | 1
MySQL & SQL Server | Relational Databases | N/A |  |  | 1
AWS Lamda Functions | Cloud services built with AWS Lamda and API Gateway | Python | Programming language |  | 1
API to Facebook/Twitter/Instagram | Connector to the Facebook/Twitter/Instagram | N/A |  | 1
boofCV | Back-End | Java | Programming language |  | 1
openCV | Back-End | Java | Programming language |  | 1
Google Tensor Flow | Back-End | Python | Programming language |  | 1
Deep Learning for Java | Back-End | Java | Programming language |  | 1
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
N/A | N/A |  | N/A

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Negotiate with the Win Conditions in the winbook
2 | Continue to read materials about image processing algorithm and machine learning algorihtm
3 | Prepare for the win condition report
4 | Determine the high-risk items for building the prototype
5 | Prepare for the prototype Presentation
6 | Learn ReactJS, Spring Boot
B. | List dependencies or things/decision that you waiting for in this week
1 | More materials from our clients including their system infrastructure and code samples
2
3
4
5
C. | List your accomplishments from the previous week
1 | Prepared for the Github repository and Google Drive
2 | Confirmed everyone's 2nd role and responsibilities
3 | Finished the Client Interaction Report
4 | Prepared for the Jira, clarify the subtask for everyone
5 | Prepared for the 1st Win-win negotiation
6 | 1st Win-Win negotiation (took note and filled the sheet)
7 | Designed and built team website
8 | Leart ReactJS and began to decide the COTS we want to use
9 | Read materials about image processing algorithm and machine learning algorithm, estimated each COTS
10 | Prepared for the 2nd Win-win negotiation: Winbook and homework
11 | 2nd Win-win negotiation
12 | Prepared for the Progress Report, Project plan and Risk Report