## Risk
Top Project Risks as of 09/21/2016
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
1 | N/A | All of teammates are not good at NodeJs and React Native | Personnel Shortfall | We should spend time learning it | 7 | 3 | 21 | N/A | 1
2 | N/A | Clients treated us as full-time developers but we are on-campus students so we don’t have sufficient time to develop | The time conflict | Negotiate with Clients | 5 | 6 | 30 | N/A | 1
3 | N/A | GPS perhaps not accurate | NDI conflict | Make a prototype to gain more information | 2 | 4 | 8 | N/A | 1
4 | N/A | Facebook login Integration, we don’t know whether the future version will cause any conflicts | NDI conflict | Make a prototype to gain more information | 1 | 5 | 5 | N/A | 1
5 | N/A | Algorithm complexity, We are not sure if there is an eligible recommendation algorithm for communities ranks | Insufficient knowledge | We should spend time learning it | 6 | 6 | 36 | N/A | 1
6
7
8
9
10

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Vincent had a family emergency and was unavailable. | Kept updating our progress to make sure that he could catch up with our project
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Most of our team members are not good at speaking Engish | More practice and communication
2
3
4
5