## SLOC
Team Number: | 4
Week: | 3
Program Size (SLOC) | Actual
Base | 118
Added | 3155
Deleted | 0
Modified | 0
Reused | 0
From COTS
Total New SLOC

## COTS
List of third-party components being considered for use in the system as of 10/02/2017
Component Name | Function of the component in the system | Related components |  | Component use in the system
|  | Dependency | Interaction | Black Box | White Box | Modify Code
iOS Camera | Allowed users to take a photo via their phone cameras | iOS Privacy - Camera Usage Description | When the system wants to access a user’s iPhone camera, a pop-up alert dialog will ask him/her if it is allowed. | x
iOS Photo Library | Allowed users to select a photo via their photo library | iOS Privacy - Photo Library Usage Description | When the system wants to access a user’s photo library, a pop-up alert dialog will ask him/her if it is allowed. | x
Phone Contact List | Get a users’ friends information from him/her contact list | iOS privacy - Contact List Usage Description | The app will send a notification to somebody that a user challenged already. | X
React Native | The main language for our team to implement front-end items for this project | NaN | The front-end code will be written in React Native language. |  | X
Components that were filtered in the previous week
Component Name | Rationale for filtering the component |  | Notes and References
XCode | Because we decided to create an App not only for iOS platform but also Android, Xcode with Swift is not suitable.

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Develop modules focused on win conditions priorities(Functionalities)
2 | Create All Documentations and Reports
3 | Implement More features for application
4 | Start further development of UI and backend functionatlities
5 | Prepare for ARB presentation and create slides
6 | Communicate with client to associate him with the changes made
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Result on prototypes
2 | Client feedback on what is currently developed so far
3 | Project Synchronization among the branches of team members
4
5
C. | List your accomplishments from the previous week
1 | New UI developed for application and accepted by client
2 | Swift Prototype Implementation
3 | Basic development for Populic Application using react native
4 | Interacted with clients in many meetings to compromise on issues or problems
5 | Verified application processes and ensured that project documentation is up to date
6
7
8