## Risk
Top Project Risks as of 09/21/2016
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
1 | N/A | The client always tries to change his previous or even yesterday’s idea during implementing | This project is super important for the client, he puts a lot of time in it but we are bored to change our achievement over and over. | We need to have a better plan for our project and try to make some regulations to regulate our behaviors, including client. | 10 | 3 | 30 | N/A | 2
2 | N/A | Seldom communication/interaction with den student | we don’t have change to meet in person and we found it was hard to communication with a virtual person. | We need to use Skype or any Phone meeting softwares more frequently | 9 | 3 | 27 | N/A | 2
3 | 2 | Clients treated us as full-time developers but we are on-campus students so we don’t have sufficient time to develop | Time conflict | Discuss more about what we are supposed to do in the following weeks. | 5 | 3 | 15 | We have had several negotiations already, we got to know each other better | 3
4 | 1 | Some of teammates are not good at NodeJs and React Native | Personnel Shortfall | we should spend time learning it | 2 | 5 | 10 | Some of our teammates are able to write React codes now | 3
5
6
7
8
9
10

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Vincent had a family emergency and was unavailable. | Kept updating our progress to make sure that he could catch up with our project
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Most of our team members are not good at speaking Engish | More practice and communication
2
3
4
5