## Risk
Top Project Risks as of 11/29/20176
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
1 | N/A | We are worried about the launch date | The client has many different developing teams and we don’t communicate with others. In addition, we don’t know the other teams progress to be honest | The entire team project manager should provide some opportunity to enable interaction among various teams and discuss the plan in advance of launching. | 7 | 3 | 21 | / | 1
2 | 3 | The score system may not feasible | We have expected a lot for the challenge feature but we don’t know whether it is enough attractive | 1) We should simplify the functionality 2) We should start to develop it even if we don’t have sufficient users’ feedback | 1 | 5 | 10 | We used the rank system. | 5
3 | 2 | The off-campus student may misunderstand or don’t know our project clearly. | In the past weeks, we didn’t have sufficient communication with the off-campus student so that we were afraid that whether he could understand what we were doing or not correctly. | Before the presentation day, we should talk with him in person and explain what we have done in this semester | 1 | 5 | 5 | WE have 2 rehearsals before presenting. During the meeting, we talked with him a lot and checked we are in the same pace. | 11
4
5
6
7
8
10

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Vincent had a family emergency and was unavailable. | Kept updating our progress to make sure that he could catch up with our project
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Most of our team members are not good at speaking Engish | More practice and communication
2
3
4
5