## Risk
Top Project Risks as of 09/21/2016
Rank |  | Risk Description | What causes this risk? | Risk Mitigation Action Items | P(L) 1-10 | S(L) 1-10 | RE | Rationale why the risk exposure has changed? | No. of Weeks Active
This Week | Last Week
1 | 4 | The score system may not feasible | We have expected a lot for the challenge feature but we don’t know whether it is enough attractive | We should interview and gather more user feedback before we publish this feature in the latest version | 7 | 9 | 63 | We didn’t schedule our time reasonable. | 4
2 | 2 | We perhaps fail to compelet our jobs on time (by the end of this semester) | We didn’t update our time schedule as the client requirement changes | we should be careful about the time schedule and re-arrange our time for the newest jobs. | 3 | 8 | 24 | We eliminate the database-related risk in the last two weeks. | 4
3 | 4 | The off-campus student may misunderstand or don’t know our project clearly. | we don’t have change to meet in person and we found it was hard to communication with a virtual guy. | He has started to code and we have talked a lot in Slack. we thought he should have a better understand of the problem domains and of what we are building. | 5 | 3 | 15 | We have talked with den student more frequently in Slack | 7
4 | 5 | Some of teammates are not good at NodeJs and React Native | Personnel Shortfall | we should spend time learning it | 1 | 1 | 1 | We have spent a bunch of time learning and designing front-end pages in React Native and operating MongoDB in NodeJS for backend jobs. | 7
5 | 4 | The score system may not feasible | We have expected a lot for the challenge feature but we don’t know whether it is enough attractive | We should interview and gather more user feedback before we publish this feature in the latest version | 7 | 9 | 63 | We didn’t schedule our time reasonable. | 4
6
7
8
9

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1
2
3
4
5
B. List any unavoidable defect occurred in the previous week
| Unavoidable defect | Proposed Solution
1 | Vincent had a family emergency and was unavailable. | Kept updating our progress to make sure that he could catch up with our project
2
3
4
5
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Most of our team members are not good at speaking Engish | More practice and communication
2
3
4
5